## Scrum Notes
Name | Yesterday | Today | Roadblock
Petro | Went through e-mails from previous days | Arif with Shawn and James (midnight) to go over pipeline | Time
| meetings | Team lists. Who's working on what and what roles are still require
James and shawn call with Arif
Reviewed sams work
Spoke with Andrew
James | FX revisions sent of to Dan | setting up verold fro India | duality of good and evil
| Animation ref for spins and specials | Key poses for animation
| corelated meeting | review current UI screens
sewer background
send footclan comments from Nick to India
Looking for animators
Shawn | Discussed pipeline management with James and Petro | Grab some c# code from Javier
| Completed folder structure flowchart | provide Andrew and James with UI art for review
| Coordinated with AE regarding UI | review Trello and prepare a demonstration for Monday (tracking application)
Meeting with Adelaide, Alex and Petro regarding game changes, art asset aquisitions and general update
Refine folder structure
Email Xerxes regarding Trello
Speak with Javier regarding Big Tool (asset management)
continnue work with Metaio (object recognition)
Steph | worked on control (90% finished) | got feedback from AK and implimenting
memory leak to do with shadows on iTouch4
Sam | Street level background | Continue working on Street Level background, adding more buildings
Andrew Embury | Main Menu | Equip Screen
| Level Stats | Hud
Pop Up
AR Training
Team Select